## Sheet1
Daily Deliverables and Fixes for HalaHomes
Date | Module | Work-Flow | Type | Member assigned | Status
|  | Data Structure | Devolpment | Sobin | Done
|  | DB logics |  | Shreyus | Done
2023-12-05 | User Onboarding | Login | Devolpment | Shreyus | Done
|  | Signup |  | Sobin | Done
2023-12-06 | Community | Interests page | Devolpment | Jeff, Shreyus | Done
|  | Creating Posts |  | Sobin, Vanshika | Done
|  | Displaying Posts |  |  | Done
2023-12-07 | Community | Adjusting the time stamps for posts | Devolpment | Sobin | Done
| Landing Page | Navbar fixes for Landing Page | Fixes | Jeff | Done
| Data-base uptate | Entering Community Posts | Update | Vanshika Chenna | Done
2023-12-08 | Community | Post expansion | Devolpment | Sobin | Done
|  | Making posts dynamic |  | Shreyus | Done
2023-12-09 | Community | Like/Dislike | Devolpment | Sobin, Shreyus | Done
|  | Adding Comment section to posts |  | Shreyus | Done
|  | Fixing responsiveness issues in server | Fixes | Jeff, Vanshika | Done
2023-12-11 | Community | Rearranging posts based on timestamp | Devolpment | Sobin | Done
|  | Adding comments |  |  | Done
|  | Pagination of posts |  |  | Done
|  | Displaying comments |  | Shreyus | Done
|  | Uploading source file to Hala_Homes_V1 |  |  | Done
|  | Adding Dynamicity to minor elemnts | Fixes | Jeff, Vanshika | Done
2023-12-12 | Community | View Counter | Devolpment | Sobin | Ongoing
|  | Like/Save in comments |  |  | Ongoing
|  | Reporting and blocking user |  |  | Ongoing
| User Profile | Dynamic Profile | Devolpment | Shreyus | Ongoing
| Community | No comments fix | Fixes | Jeff | Ongoing
|  | Interest page fixes |  |  | Ongoing
| User Onboarding | Login/Signup fixes |  |  | Ongoing
| Data-base uptate | Updating user names | Fixes | Vanshika Chenna | Ongoing